## Sheet1
No | Title | Display list of items in the store. |  |  | Estimation (Days) | Priority
1 | Login/Sign in Page | User will able to login to their account. |  |  | 10 Days | 10
2 | Catalog | Display list of items in the store. |  |  | 15 Days | 10
3 | Specify Color | User are able to choose their shirt color. |  |  | 2 Days | 10
4 | Size Measurement | User are able to choose their shirt size. |  |  | 2 Days | 10
5 | Pay Online | User will be able to pay using online payment method. |  |  | 12 Days | 10
6 | Delivery Service | User are able to provide their delivery address to have the product delivered to them. |  |  | 5 Days | 10
7 | Shopping Cart | User will be able to checkout multiple items that they picked. |  |  | 7 Days | 20
8 | Request Specific Design | User will be able to request for their own design personally to the owner of the business. |  |  | 2 Days | 30
9 | Purchase History | User are able to view their purchase history. |  |  | 7 Days | 40
10 | Virtual Assistant | User are able to interact with a virtual assistant service if they have any problem or question regarding the website/services. |  |  | 15 Days | 50
Iteration 1 |  |  | Iteration 2 | Iteration 3
25
0
20
15
10
5
0
Work Left
Days Left
28
0
20
15
10
5
0
Work Left
Days Left
31
0
20
15
10
5
0
Work Left
Days Left